VECTOR EQUINE  ·  MILESTONE 1, SECTION A

Transcription Quality

A1 audit findings, and why the section has to be resequenced

A1 is complete. Every question in the audit task is answered below with file paths and line numbers, and no code has been changed. The brief said to report before starting A2, so this is that report — plus the consequences, because three of them change the plan.

| Headline | Detail |
| --- | --- |
| Audio has never been kept | Nothing in the codebase writes an audio_recording asset. Mic chunks are transcribed in memory and discarded. A3 and A4 cannot run against any existing session. |
| There is no raw transcript | Cleanup runs inside the transcription call, again on insert, and the journal step then overwrites the row. Three mutation sites, no original preserved. |
| Real speech is being deleted | The cleanup drops whole segments, including any utterance of twelve characters or less matching common words. A trainer saying No. is discarded before storage. |
| Terminology is being rewritten | haunches in becomes haunches-in, twenty meter becomes 20m, unconditionally, before the row is written. This is the exact risk A2 was written to prevent, already happening. |
| A5 and A6 are adversarial | The codebase already discovered that prompt content leaks back as fake transcript. Expanding the lexicon will likely worsen the problem A5 exists to fix. |
| A7 is largely already done | Audio is never mixed before transcription. Speaker attribution is structural, from which device posted the chunk. |

### What this document is for

Sections 1 and 2 are the audit report the brief asked for. Section 3 is what the findings change, as numbered items C1 to C5 with a response box each. Section 4 is the revised task order. Section 5 has the four decisions needed before code starts.

# 1 · A1 audit — the six questions, answered

| Question | Answer | Evidence |
| --- | --- | --- |
| Which Whisper implementation | OpenAI hosted API, model whisper-1, called over REST. Base URL is api.openai.com when OPENAI_API_KEY is set, otherwise the Vercel gateway. No local model, no faster-whisper, no whisper.cpp. | src/lib/capture/whisper.ts 103-152 |
| Is raw output persisted separately from the cleaned version? | No. There is no raw artifact anywhere. See C1 for the three places text is modified. | whisper.ts 179; apply-whisper-bytes.ts 80; polish/route.ts 192-193 |
| Do rows record which model produced them? | Partially, and unreliably. raw_json.engine and raw_json.model are hardcoded string literals, not read from the response. No prompt version, no VAD parameters, no cloud-or-device marker. | apply-whisper-bytes.ts 83-88; apply-whisper.ts 131-135 |
| One mixed track or separate per participant? | Separate, already. Each phone posts its own mic chunks through one client code path; the rider sends with a session cookie and the trainer with a guest token. | capture-room.tsx 1402; audio/route.ts 28-74 |
| How is speaker attribution determined? | Structurally, from the auth path. Guest token means trainer, session cookie means rider. No diarisation anywhere in the codebase. A second path infers speaker from the storage path when re-transcribing. | audio/route.ts 33-74; apply-whisper.ts 10-14 |
| Do recorded sessions still have their audio? | No. See section 2 — this is the finding that reorders the plan. | audio/route.ts 18-19 |

## Tables and columns, for the record

Transcript text lives in session_transcript_segments: offset_ms, ended_offset_ms, speaker (rider / trainer / system / vector), text, confidence, raw_json, client_id, plus addressed_to_vector and excluded_from_corpus added later. Defined in migration 20260721000000_capture_pipeline.sql lines 27-40.

Audio and video would live in session_media_assets: kind constrained to video | sensor | audio_recording, storage_path, sync_offset_ms. The private bucket is session-videos. No audio_recording row is ever created.

# 2 · The finding that reorders the section

BLOCKING · RESEQUENCES A3 AND A4

session_media_assets.kind permits audio_recording, and one place in the codebase queries for it. Nothing ever writes it. Mic chunks arrive, go to Whisper in memory, and are dropped on the floor. The route says so:

/** * Accept a mic chunk, Whisper it, return segments when ready. * Storage skipped — bucket create was stalling lab rides. */ src/app/api/capture/sessions/[id]/audio/route.ts, lines 17-19

A chunkPath string is computed and stored in raw_json.chunk_path, which makes it look as though audio was saved. Nothing uploads the bytes.

### Two consequences

The re-transcription path is dead code. applyWhisperTranscript queries session_media_assets for audio_recording rows, finds none, and returns early on every call. It has never done anything in production.

A3 and A4 cannot run against sessions already recorded. The harness needs a session's audio. The baseline needs Rhen hand-correcting a reference against audio he can listen to. For every session captured so far, the transcript is the only artifact that survives — and the transcript is the thing under investigation.

You cannot measure the error rate of a transcript when the audio it came from is gone.

So the brief's opening claim — that this section can start immediately against sessions already recorded — does not hold. Audio retention has to land first, and a fresh session has to be recorded before there is anything to measure.

### One check to run before accepting this

List the session-videos bucket under the capture-audio/ prefix. An earlier build may have uploaded files without creating asset rows. This could not be checked from a read-only audit as it needs live credentials. If files are there, the picture improves considerably and A4 may be possible on a real historical session, which would be much better than a staged one.

RESPONSE · BUCKET CONTENTS

# 3 · What the findings change

## C1 · A2 is a refactor, not a schema addition. Cleanup is inside ingest.

HIGH · LARGER THAN THE BRIEF ASSUMES

### What the brief assumes

That cleanup is a later step which can be separated from the raw output, and that if both are already stored the task reduces to enforcing a rule and adding a test.

### What is actually happening

Text is modified in three places, and the first one is inside the transcription function itself:

| Where | What it does |
| --- | --- |
| whisper.ts 179 | cleanAsrText is applied inside transcribeLessonAudio, before the segment is ever returned. Adding a raw column today would capture already-cleaned text. |
| apply-whisper-bytes.ts 80 | cleanAsrText applied a second time on the way into the insert. |
| polish/route.ts 192-193 | The journal step issues .update({ text, raw_json }) against the stored rows — an in-place overwrite of the only copy. |

### Why this is urgent rather than merely wrong

The cleanup is destructive in exactly the ways the brief warns about, and it is running on every session recorded right now.

Whole segments are deleted, not flagged. isWhisperHallucination causes cleanAsrText to return an empty string, and empty rows are filtered out before insert. One rule drops any utterance of twelve characters or less matching a list of common words — so a trainer saying No. or Yes. is silently discarded.

Terminology is normalised unconditionally. haunches in to haunches-in, half halt to half-halt, twenty meter to 20m. Defensible as display text. Not defensible as a training label, because the label no longer records what was said.

A real instruction can be dropped as a prompt echo. VOCAB_DUMP_RE discards any text containing walk, trot and canter together — which is a plausible thing for a trainer to say.

Three quality signals are computed and thrown away. Whisper returns no_speech_prob, avg_logprob and compression_ratio per segment. They are used as filters at whisper.ts 167-178 and then discarded. These are precisely the numbers A3 needs.

### Proposed split

A2a — stop the loss. Move cleanAsrText out of transcribeLessonAudio so the unmodified Whisper text is what gets stored, and persist the three discarded signals in raw_json. Small, mechanical, no schema migration required.

A2b — the separation and the test. Cleaned text becomes its own record, polish stops updating in place, and a test fails if any code path mutates a raw row.

Recommendation: A2a is done first, ahead of everything including the harness. Every session recorded between now and then loses speech that cannot be recovered, and the change is hours rather than days.

RESPONSE

## C2 · A5 and A6 work against each other, and the codebase already learned this.

HIGH · CHANGES A6 ACCEPTANCE

### What already exists

A vocabulary prompt is already in place, roughly twenty terms, hardcoded in TypeScript at whisper.ts 16-19 and passed on every request. So A6 is partly built. Directly above it sits a warning earned the hard way:

/** * Whisper `prompt` is prior-text bias — never put "Hey Vector" or instructions * here; Whisper echoes them into silence as fake transcript / false wakes. */ src/lib/capture/whisper.ts, lines 12-15

And there is a dedicated regular expression, VOCAB_DUMP_RE in asr-cleanup.ts 47-48, whose entire job is catching Whisper regurgitating that vocabulary prompt back as transcript.

### The problem

A6 asks for the prompt to be expanded toward the 224-token ceiling. On this evidence that will increase phantom text during silence — the exact failure mode A5 exists to eliminate. The brief treats the two tasks as independent. They are coupled and they pull in opposite directions.

### Proposed change to A6

A6 runs after A5, never before, so voice activity detection is already suppressing the silence the prompt would otherwise be echoed into.

A6's acceptance requires two numbers, not one: lexicon term accuracy must improve and the non-speech insertion rate must not regress. A prompt that fixes terminology while reintroducing phantom text is a net loss for labeling.

Prompt length is treated as a tunable to be measured, not a budget to be filled. Start from the twenty terms already in place and add in small increments, measuring both numbers each time.

RESPONSE

## C3 · A7 is mostly already satisfied.

LOW · REDUCES SCOPE

Audio is never mixed before transcription. Each phone posts its own mic chunks through one client path at capture-room.tsx 1402, and the speaker is decided by which credential the request carried — guest token means trainer, session cookie means rider. Attribution is structural, and no diarisation exists anywhere in the codebase.

### What is actually left

Write the never-mix rule down as a test, so it cannot be undone by accident later.

Decide what happens at tier 2, when the device is in the audio path. If the box ever produces a single mixed recording, this invariant breaks — and that is a design constraint on the device work, not on this section.

Note that the speaker column also accepts system and vector, so anything reading the corpus needs to exclude synthetic rows. excluded_from_corpus already exists for this.

RESPONSE

## C4 · A8 should move early, because it is nearly free once A2a is open.

SEQUENCING

A8 asks that model, VAD parameters, lexicon version and producing path all be retrievable per transcript. Today raw_json carries two hardcoded literals and nothing else.

Once A2a is already editing the write path, adding these is a few lines. Doing it later means reopening the same code and, worse, means the A4 baseline is recorded without provenance — so the one measurement everything is compared against would be the only one that cannot be traced to its configuration.

One correction to how it is written today: the model must be recorded from the actual request or response, not as a string constant. A hardcoded "whisper-1" will keep reporting whisper-1 after somebody changes the model, which is worse than recording nothing.

RESPONSE

## C5 · The baseline session has to be recorded before A3 and A4 can start.

BLOCKING · SCHEDULING, NOT ENGINEERING

Because no audio survives, A4's reference transcript has to come from a session recorded after A0 lands. That has three practical consequences worth planning around rather than discovering.

It gates the measurable work. A3 can be written against a synthetic fixture, but A4, A5 and A6 all need one real session with real arena noise and both voices.

It makes the microphone question unavoidable, which is good. The brief notes that if the audio is audibly poor to a human, the problem is the microphone and no model work will fix it. Recording fresh means that check happens before any effort is spent on models.

Whatever is used becomes the baseline. Every later number is compared against this recording, so the hardware and placement should be the intended production setup rather than whatever is nearest to hand.

RESPONSE

# 4 · Revised task order

Two structural changes: a new A0 for audio retention ahead of the harness, and A2 split so the destructive part stops immediately. Everything else keeps the brief's intent.

| Order | Task | Depends on | Note |
| --- | --- | --- | --- |
| A2a | Move cleanup out of the transcription call; store unmodified Whisper text; persist no_speech_prob, avg_logprob, compression_ratio | Nothing | Do this first. Every session recorded before it loses speech permanently. |
| A0 | Persist mic chunks to storage and write audio_recording asset rows | Bucket check | Revives applyWhisperTranscript as a side effect. Prerequisite for all measurement. |
| A8 | Record model, prompt version, VAD parameters and producing path per row, read from the real request | A2a | Nearly free while A2a is open. Must land before the baseline. |
| A7 | Write the never-mix invariant as a test | Nothing | Mostly already true. Parallelisable. |
| A2b | Cleaned text as a separate record; polish stops updating in place; test that fails on raw mutation | A2a | The full separation the brief asked for. |
| A3 | Measurement harness, three numbers, file output | A0 | Can be written against a fixture while waiting for a recorded session. |
| A4 | Baseline on a newly recorded session, 15-20 minutes, both voices, real noise | A0, A3, A8 | Also the microphone sanity check. |
| A5 | Silero VAD ahead of upload. New code — the hosted API means there is no configuration flag. | A4 | Also reduces cost by not uploading silence. |
| A6 | Lexicon file, versioned, editable without a code change; incremental expansion | A5 | Acceptance now requires two numbers. See C2. |

### What can run in parallel

A2a, A7 and the bucket check need nothing and can start together. A3 can be built against a synthetic fixture while the baseline session is being arranged. A0 is the only hard gate, and everything from A4 onward sits behind it plus one recorded ride.

RESPONSE · AGREE, OR REORDER

# 5 · Decisions needed before code starts

## Q1 · Is there audio in the bucket, or do we accept that the baseline needs a fresh recording?

This decides whether measurement starts now or after a ride. It is a one-command check and nothing downstream can be scheduled without the answer.

RESPONSE

## Q2 · Does A2a get pulled ahead of everything as an urgent fix?

The pipeline is currently deleting real speech and rewriting terminology on every session. My recommendation is yes: sessions recorded between now and the fix are unrecoverable, and the change is small. The counter-argument is that it reorders an agreed brief.

RESPONSE

## Q3 · Given the prompt-echo evidence, does A6 still aim for the 224-token ceiling?

The codebase has already been burned by prompt content appearing as transcript. Proposal is to treat prompt length as a measured variable rather than a budget, and to gate A6 on the insertion rate holding.

RESPONSE

## Q4 · Who records the baseline session, on what microphone, in which arena?

Whatever is used defines the baseline every later number is compared against, and it doubles as the microphone quality check. Worth choosing deliberately rather than defaulting to whatever is available.

RESPONSE

# Appendix · Evidence index

| Reference | What it shows |
| --- | --- |
| src/lib/capture/whisper.ts 12-15 | The warning that prompt content echoes back as fake transcript. |
| src/lib/capture/whisper.ts 16-19 | The existing twenty-term vocabulary prompt, hardcoded. |
| src/lib/capture/whisper.ts 139-143 | Hosted OpenAI call: whisper-1, temperature 0, verbose_json, prompt attached. |
| src/lib/capture/whisper.ts 167-178 | The three quality signals used as filters and then discarded. |
| src/lib/capture/whisper.ts 179 | cleanAsrText applied inside transcription, before anything is returned. |
| src/lib/capture/asr-cleanup.ts 5-34 | PHRASE_FIXES — unconditional terminology rewriting. |
| src/lib/capture/asr-cleanup.ts 47-48 | VOCAB_DUMP_RE — drops text containing walk, trot and canter together. |
| src/lib/capture/asr-cleanup.ts 74-81 | The rule that deletes utterances of twelve characters or less. |
| src/app/api/capture/sessions/[id]/audio/route.ts 17-19 | “Storage skipped” — the reason no audio exists. |
| src/app/api/capture/sessions/[id]/audio/route.ts 33-74 | Speaker decided by credential: guest token means trainer. |
| src/app/api/capture/sessions/[id]/polish/route.ts 192-193 | In-place update of stored transcript text. |
| src/lib/capture/apply-whisper.ts 49-62 | The dead query for audio_recording assets. |
| src/lib/capture/apply-whisper.ts 104-108 | Deletes all segments for a re-transcribed speaker. |
| src/lib/capture/apply-whisper-bytes.ts 59-72 | Deletes non-Whisper segments inside a time window. |
| src/components/capture/capture-room.tsx 1402 | The single client path both phones use to post mic audio. |
| supabase/migrations/20260721000000_capture_pipeline.sql 27-56 | Transcript and media asset tables. |

Vector Equine · Milestone 1 Section A · A1 audit and revised plan · 29 August 2026 · No code changed in producing this report.